## Overall Total jan-dec
			Kolin Philippines International,Inc.
			Kolin Bldg.Sta.Rita St.,Guadalupe Nuevo
			Makati City,Metro Manila

			Overall Total PRF Request (January to December 2025)
			(Regular & Irregular)

PRF RECEIVED	JANUARY	FEBRUARY	MARCH	APRIL	MAY	JUNE	JULY	AUGUST	SEPTEMBER	OCTOBER	NOVEMBER	DECEMBER	TOTAL
Head Office	62	63	68	27	65	43	53	57	42	62	40	22	604
Cavite Plant	19	23	15	23	12	23	18	18	22	18	12	8	211
Cebu Service Center	2	0	1	1	0	0	0	1	0	1	0	1	7
Ilo-Ilo service Center	2	1	3	0	0	1	1	1	5	2	2	1	19
Pampanga Service Center	1	5	0	3	1	2	3	0	4	0	0	2	21
Davao Service Center	3	3	2	1	3	3	0	3	1	1	0	1	21
Bacolod Service Center	1	1	1	0	1	1	1	2	0	0	1	0	9
Cagayan De Oro Service Center	0	0	0	1	1	0	0	3	1	0	2	0	8
Dagupan Service Center	0	0	1	0	1	1	0	3	3	2	1	0	12
From January to December 2025	90	96	91	56	84	74	76	88	78	86	58	35	912

## December
DATE ADMIN RECEIVED	PRF NO.	REQUISITIONING DEPARTMENT	ITEM DESCRIPTION	ADMIN LEADTIME AFTER DATE RECEIVED	ACTUAL PO ISSUED DATE	NO. OF DAYS PROCESSED	RATING %	PRF PROCESSED	DATE FAXED TO SUPPLIER	ACTUAL DELIVERY DATE	NO. OF DAYS PROCESSED (from Date Fax to Supplier to Actual Delivery of Item)	Status/Remarks
27-Nov-25	14187	H.O. MARKETING	5,000pcs. FREE KETTLE STICKER	12 days	16-Dec-25	12	100%	OK	16-Dec-25	8-Jan-26	12	OK
12-Dec-25	14135	H.O. MARKETING	DISPLAY RACK for J&R IMUS	12 days	16-Dec-25	2	100%	OK	16-Dec-25
12-Dec-25	14196	H.O. MARKETING	DISPLAY BASEDBOARD for WESTERN FISHERMALL	12 days	16-Dec-25	2	100%	OK	16-Dec-25	12-Jan-26	14	OK
15-Dec-25	14207	H.O. ADMIN	6,100pcs. QUAD AI POP	12 days	17-Dec-25	2	100%	OK	17-Dec-25	4-Feb-26	30	OK
16-Dec-25	00466	PAMPANGA SALES	DISPLAY RACK for 1st MEGA SAVER CAPAS TARLAC	12 days	17-Dec-25	1	100%	OK	17-Dec-25
15-Dec-25	14169	H.O. AIS	TEMPORARY PARTS WITHDRAWAL RECEIPT (TPWR) H.O./ PARTS TRANSFER RECEIPT (PTR) 7 province	12 days	19-Dec-25	4	100%	OK	19-Dec-25	14-Jan-26	13	OK
15-Dec-25	14169	H.O. AIS	PROPETY OUT PASS (H.O.)/ EXPENSE REPORT/ STOCK CARDS	12 days	19-Dec-25	4	100%	OK	19-Dec-25	21-Jan-26	18	OK
15-Dec-25	3059	CAVITE PLANT	STOCK TRANSFER FORM (STF) #30001-32500	12 days	19-Dec-25	4	100%	OK	19-Dec-25	21-Jan-26	18	OK
15-Dec-25	3062	CAVITE PLANT	22pairs SAFETY SHOES (ALLOY/ AD200 S3)	12 days	19-Dec-25	4	100%	OK	19-Dec-25	7-Jan-26	13	OK
22-Dec-25	3060	CAVITE PLANT	100pads PARTS TRANSFER RECEIPT - CAV.	12 days	6-Jan-26	6	100%	OK	6-Jan-26	16-Jan-26	8	OK
23-Dec-25	00469	CEBU SERVICE	ELECTRICAL SYSTEM INSTALL in CEBU OFFICE	12 days	5-Jan-26	4	100%	OK	6-Jan-26
29-Dec-25	14170	H.O. AIS	TEMPORARY DELIVERY RECEIPT - BACOLOD	12 days	5-Jan-26	2	100%	OK	6-Jan-26
29-Dec-25	14205	H.O. O.P.	CALIBRATION of TOOLS & EQUIPMENT	12 days	5-Jan-26	2	100%	OK	6-Jan-26	29-Jan-26	17	OK